## Wagons
Takt train — wagon catalog (anonymized pattern)
One row per wagon = one reusable work package that the train repeats in every takt zone. Takt beat = 1 week.
Wagon | Crew | Activity (generic trade) | Unit
3 | SUB-01 | Survey & layout — wall set-out | AREA
3 | SUB-02 | Core drilling — penetrations | COUNT
5.1 | SUB-03 | Drywall — first-side boarding | AREA
5.2 | SUB-04 | MEP in-wall — conduit & pipework | AREA
5.3 | SUB-03 | Drywall — second-side / close-up | AREA
6.1 | SUB-06 | Painting — filling & first coat | AREA
7 | SUB-07 | Suspended ceiling — grid & boards | AREA
8 | SUB-08 | Sprinkler — mains & drops | AREA
9 | SUB-09 | Ventilation — ducts & terminals | AREA
10 | SUB-05 | Plumbing — mains, branches, pressure test | AREA
11.1 | SUB-04 | Electrical — cable trays / close-up | AREA
12.1 | SUB-04 | Electrical — cabling & distribution boards | AREA
13 | SUB-04 | Electrical — data & fire-alarm cabling | AREA
14 | SUB-11 | BMS / security / IT — cabling | AREA
17.1 | SUB-06 | Painting & tiling — wet rooms, final coats | AREA
18 | SUB-14 | Flooring — levelling & finishes | AREA
20.1 | SUB-16 | Joinery — kitchenette, doors, trims | COUNT
21 | SUB-11 | MEP/BMS — fit-out completion | AREA
22 | SUB-04 | Commissioning — electrical & controls | AREA
23 | SUB-19 | Final cleaning & handover | AREA

## Zones
Takt zones — building B
Zone code = building : floor : zone. Areas are illustrative (the ontology derives real areas from TopologicPy geometry).
Zone | Building | Floor | Sub-zone | Area m² (illustrative)
B5:1 | B | Plan 5 | 1 | 184
B5:2 | B | Plan 5 | 2 | 176
B4:1 | B | Plan 4 | 1 | 179
B4:2 | B | Plan 4 | 2 | 181
B2:1 | B | Plan 2 | 1 | 171
B2:2 | B | Plan 2 | 2 | 168

## Flowline
Flowline — building B (takt zone × takt week)
Each cell = the wagon occupying that zone that week. Read a diagonal band: the train walks zone-to-zone, one takt apart. Blanks = buffer / no work. Time is relative takt weeks (T01…); real calendar removed.
Zone | T01 | T02 | T03 | T04 | T05 | T06 | T07 | T08 | T09 | T10 | T11 | T12 | T13 | T14 | T15 | T16 | T17 | T18 | T19 | T20 | T21 | T22 | T23 | T24 | T25 | T26 | T27 | T28 | T29 | T30 | T31 | T32 | T33 | T34 | T35 | T36 | T37 | T38 | T39 | T40 | T41 | T42 | T43 | T44 | T45 | T46 | T47 | T48 | T49 | T50 | T51 | T52 | T53 | T54 | T55 | T56 | T57 | T58 | T59
B5:1 | 3 |  |  | 5.1 | 5.2 | 5.3 | 6.1 | 7 | 8 | 9 | 9 | 10 | 10 | 11.1 | 12.1 | 13 | 14 | 17.1 | 21 | 18 |  | 18 |  |  | 20.1 | 22 | 23 | 23
B5:2 | [5 empty] | 3 |  | 5.1 | 5.2 | 5.3 | 6.1 | 7 | 8 | 9 | 9 | 10 | 10 | 11.1 | 12.1 | 13 |  |  | 14 | 17.1 | 21 | [9 empty] | 18 | 18 |  | 20.1 | 22 | 23 | 23
B4:1 | [22 empty] | 3 |  | 5.1 | 5.3 | 6.1 | 7 | 8 |  |  |  |  | 9 | 9 | 6.1 | 10 | 10 | 11.1 | 12.1 | 13 | 14 | 17.1 | 21 | 21 | 18 | 18 | 20.1 | 20.1 | 20.1 |  | 22 | 23
B4:2 | [22 empty] | 3 | 5.1 | 5.3 | 6.1 | 7 | 8 | 9 |  |  |  |  | 9 | 10 | 10 | 11.1 | 12.1 | 13 |  | 14 | 17.1 | 21 | 21 | 18 | 18 | 20.1 | 20.1 |  |  |  | 22 | 23
B2:1 | [27 empty] | 3 | [5 empty] | 5.1 |  |  |  | 5.3 | 6.1 | 8 | 9 | 9 | 10 | 10 | 11.1 | 12.1 | 13 |  | 14 | 17.1 | 21 |  | 18 |  | 18 | 18 | 20.1 | 20.1 | 23
B2:2 | [27 empty] | 3 | 5.1 |  |  |  |  | 5.3 |  | 6.1 | 7 | 8 | 9 | 9 | 10 | 10 | 11.1 | 11.1 | 12.1 | 12.1 | 13 | 14 | 17.1 | 21 |  | 18 | 18 |  |  | 20.1 | 20.1 | 20.1 | 23

## Legend
Anonymized takt-flowline pattern
This workbook is a SMALL, fully anonymized slice of a real takt production plan,
extracted as a discussion pattern for the taktology ontology.
What it shows (the takt method in three tables):
- Wagons = the takt train: reusable work packages, in sequence, 1-week beat.
- Zones = the locations the train moves through (building : floor : sub-zone).
- Flowline = wagon x zone x time; the diagonal band is the train walking the zones.
Anonymization applied:
- Project / client / estate names, project number, and named third parties removed.
- Subcontractor codes remapped 1:1 to neutral SUB-01..SUB-20 (flowline relations intact).
- Swedish activity text replaced with generic English trade labels.
- Original calendar replaced with relative takt weeks T01..; buffers preserved.
- Wagon ids and zone coordinates are generic and kept (they carry the structure).
Maps to ontology/takt.ttl: WagonType (a Wagons row) is instantiated as a TaktTask
(a Flowline cell) performedIn a TaktZone (a Zones row), performedBy a Crew (SUB-xx),
chained by hasSuccessor. See examples/takt-flowline-demo.md.